## Week 1 Task List
Story ID | Task ID | Task | Week | Status | Assignee | Estimated Effort | Effort | Peer Reviewed | Feature File
SETUP | [7 empty] | TRUE | N/A
| T01 | Create Umple class model | 1 | Complete | Everyone | 1 hr | 1.5 hrs
| T02 | Create CRUD Repositories | 1 | Complete | Everyone | 1 hr | 1 hr
| T03 | Test CRUD Repositories (unit) | 1 | Complete | Everyone | 30 min | 45 min
| T04 | Decide what pages/views should different users see. | 1 | Complete | Everyone | 30 min | 30 min
| T05 | Create frontend mock up of each page/view that a user can see | 1 | Complete | Dan, Mircea | 3 hrs | 3 hrs
| T06 | Implement the mock ups of each page/views. | 1 | Complete | Everyone | 1 hr | 2 hrs
| T07 | Create Vue project. | 1 | Complete | Mircea | 2 hrs | 3 hrs
US001 | [7 empty] | TRUE | CreateAccountUS001.feature
| T01 | Create Gherkin Script | 1 | Complete | Majid | 45 min | 1.5 hr
| T02 | Create account creation frontend page | 1 | Complete | Majid | 2 hrs | 3 hrs
| T03 | Include scripts and logic for webpage to create account | 1 | Complete | Majid | 1.5 hrs | 1.5 hrs
| T04 | Run unit tests & Gherkin | 1 | Complete | Majid | 1 hr | 15 min
| T05 | Review Pull Request before Main branch merge | 1 | Complete | Alex | 20 min | 15 min
US002 | [7 empty] | TRUE | changePassword.feature
changeUsername.feature
| T01 | Create Gherkin Script | 1 | Complete | Ehsan | 45 min | 1 hr
| T02 | Create account edit frontend page | 1 | Complete | Ehsan, Dan | 2 hrs | 3 hrs
| T03 | Include scripts and logic for webpage to edit a user's account | 1 | Complete | Ehsan | 2 hrs | 6 hrs
| T04 | Run unit tests & Gherkin | 1 | Complete | Ehsan | 1 hr | 40 mins
| T05 | Review Pull Request before Main branch merge | 1 | Complete | Alex | 20 min | 20 mins
US003 | [7 empty] | TRUE | deleteAccount.feature
| T01 | Create Gherkin Script | 1 | Complete | Kiro & Alex | 45 min | 30 mins
| T02 | Create Delete Account Button in the Account tab page. | 1 | Complete | Mircea & Kiro | 30 mins | 10 min
| T03 | Implement backend logic to remove the account from the database. | 1 | Complete | Mircea | 1.5 hrs | 30 min
| T04 | Create a text box that takes in the user's password and only then allows the user to delete. | 1 | Complete | Kiro | 1 hr | 2 hrs
| T05 | Decide what happens to the user's NFTs when account is deleted. | 1 | Complete | Mircea | 30 min | 5 min
| T06 | Run unit tests & Gherkin | 1 | Complete | Kiro & Alex | 1 hr | 20 mins
| T07 | Review Pull Request before Main branch merge | 1 | Complete | Alex | 20 min | 10 mins
US004 | [7 empty] | TRUE | Login.feature
| T01 | Create Gherkin Script | 1 | Complete | Kalvin | 45 min | 1 hr
| T02 | Create a login page for users to login with their email. | 1 | Complete | Kalvin | 2 hrs | 2 hrs
| T03 | Implement logic to query if the user email exists in the database. | 1 | Complete | Kalvin | 2 hrs | 2.5 hrs
| T04 | If user email exists in database, check if the password entered is correct. | 1 | Complete | Kalvin | 30 min | 30 mins
| T05 | Display a message in the case of invalid username/password. | 1 | Complete | Hong Yi | 45 min | 1 hr
| T06 | Display a message in the case an account is locked out | 1 | Complete | Hong Yi | 45 min | 1 hr
| T07 | Implement logic to bring the user to their account home page. | 1 | Complete | Hong Yi | 1.5 hrs | 2 hrs
| T08 | Run unit tests & Gherkin | 1 | Complete | Hong Yi | 1 hr | 3 hrs
| T09 | Review Pull Request before Main branch merge | 1 | Complete | Seb | 20 min | 20 mins
US005 | [7 empty] | TRUE | LogOutUS005.feature
| T01 | Create Gherkin Script | 1 | Complete | Harsh | 45 min | 40 mins
| T02 | Create a logout button on top nav menu | 1 | Complete | Harsh | 30 mins | 40 mins
| T03 | Implement backend logic to log out the current user and return to login | 1 | Complete | Harsh | 2 hrs | 1.5 hrs
| T04 | Run unit tests & Gherkin | 1 | Complete | Harsh | 1 hr | 3 hrs
| T05 | Review Pull Request before Main branch merge | 1 | Complete | Alex | 20 min | 10 mins