## Sprint A Backlog
Story ID | User Story Description | Task ID | Task | Week | Status | Peer Reviewed
SETUP | Setup (every developer) |  |  |  |  | TRUE
|  | T01 | Create Umple class model | 1 | Complete
|  | T02 | Create CRUD Repositories | 1 | Complete
|  | T03 | Test CRUD Repositories (unit) | 1 | Complete
|  | T04 | Decide what pages/views should different users see. | 1 | Complete
|  | T05 | Create frontend mock up of each page/view that a user can see | 1 | Complete
|  | T06 | Implement the mock ups of each page/views. | 1 | Complete
|  | T07 | Create Vue project. | 1 | Complete
US001 | "As a user, I would like to be able to create a NF-TEA Marketplace account." |  |  |  |  | TRUE
|  | T01 | Create Gherkin Script | 1 | Complete
|  | T02 | Create account creation frontend page | 1 | Complete
|  | T03 | Include scripts and logic for webpage to create account | 1 | Complete
|  | T04 | Run unit tests & Gherkin | 1 | Complete
|  | T05 | Review Pull Request before Main branch merge | 1 | Complete
US002 | "As a user, I would like to be able to edit my NF-TEA Marketplace account details." |  |  |  |  | TRUE
|  | T01 | Create Gherkin Script | 1 | Complete
|  | T02 | Create account edit frontend page | 1 | Complete
|  | T03 | Include scripts and logic for webpage to edit a user's account | 1 | Complete
|  | T04 | Run unit tests & Gherkin | 1 | Complete
|  | T05 | Review Pull Request before Main branch merge | 1 | Complete
US003 | "As a user, I would like to be able to delete my NF-TEA Marketplace account." |  |  |  |  | TRUE
|  | T01 | Create Gherkin Script | 1 | Complete
|  | T02 | Create Delete Account Button in the Account tab page. | 1 | Complete
|  | T03 | Implement backend logic to remove the account from the database. | 1 | Complete
|  | T04 | Create a text box that takes in the user's password and only then allows the user to delete. | 1 | Complete
|  | T05 | Decide what happens to the user's NFTs when account is deleted. | 1 | Complete
|  | T06 | Run unit tests & Gherkin | 1 | Complete
|  | T07 | Review Pull Request before Main branch merge | 1 | Complete
US004 | "As a registered user, I would like to be able to login to my NF-TEA Marketplace account." |  |  |  |  | TRUE
|  | T01 | Create Gherkin Script | 1 | Complete
|  | T02 | Create a login page for users to login with their email. | 1 | Complete
|  | T03 | Implement logic to query if the user email exists in the database. | 1 | Complete
|  | T04 | If user email exists in database, check if the password entered is correct. | 1 | Complete
|  | T05 | Display a message in the case of invalid username/password. | 1 | Complete
|  | T06 | Display a message in the case an account is locked out | 1 | Complete
|  | T07 | Implement logic to bring the user to their account home page. | 1 | Complete
|  | T08 | Run unit tests & Gherkin | 1 | Complete
|  | T09 | Review Pull Request before Main branch merge | 1 | Complete
US005 | "As a registered and logged-in user, I would like to be able to logout from my NF-TEA Marketplace account." |  |  |  |  | TRUE
|  | T01 | Create Gherkin Script | 1 | Complete
|  | T02 | Create a logout button on top nav menu | 1 | Complete
|  | T03 | Implement backend logic to log out the current user and return to login | 1 | Complete
|  | T04 | Run unit tests & Gherkin | 1 | Complete
|  | T05 | Review Pull Request before Main branch merge | 1 | Complete
US006 | "As a registered and logged-in user, I would like to be able to link my MetaMask wallet to my NF-TEA account." |  |  |  |  | TRUE
|  | T01 | Create Gherkin Script | 2 | Complete
|  | T02 | Add Metamask library to frontend. | 2 | Complete
|  | T03 | Create connect to Metamask button on the frontend. | 2 | Complete
|  | T04 | Create success/failure popup on the frontend. | 2 | Complete
|  | T05 | Run unit tests & Gherkin | 2 | Complete
|  | T06 | Review Pull Request before Main branch merge | 2 | Complete
US007 | "As a registered and logged-in user, I would like to be able to link one or more Instagram accounts to my NF-TEA account." |  |  |  |  | TRUE
|  | T01 | Create Gherkin Script | 2 | Complete
|  | T02 | Create Facebook NF-Tea project on Facebook API page | 2 | Complete
|  | T03 | Add all team members to the Facebook NF-Tea project. | 2 | Complete
|  | T04 | Create Facebook API queries. | 2 | Complete
|  | T05 | Create connect to Instagram button on the frontend. | 2 | Complete
|  | T06 | Create success/failure popup on the frontend. | 2 | Complete
|  | T07 | Run unit tests & Gherkin | 2 | Complete
|  | T08 | Review Pull Request before Main branch merge | 2 | Complete
US008 | "As a registered and logged-in user, I would like to unlink my previously-linked MetaMask wallet from my NF-TEA account." |  |  |  |  | TRUE
|  | T01 | Create Gherkin Script | 2 | Complete
|  | T02 | Create frontend dialogue to unlink Metamask. | 2 | Complete
| Dependent on US006 | T03 | Implement function to communicate with Metamask for its disconnection. | 2 | Complete
|  | T04 | Create success/failure popup on the frontend. | 2 | Complete
|  | T05 | Run unit tests & Gherkin | 2 | Complete
|  | T06 | Review Pull Request before Main branch merge | 2 | Complete
US009 | "As a registered and logged-in user, I would like to unlink my previously-linked Instagram account(s) from my NF-TEA account." |  |  |  |  | TRUE
|  | T01 | Create Gherkin Script | 2 | Complete
|  | T02 | Create disconnect to Instagram button on the frontend. | 2 | Complete
| Dependent on US007 | T03 | Create frontend dialogue to unlink Instagram. | 2 | Complete
|  | T04 | Create Facebook API disconnect queries. | 2 | Complete
|  | T05 | Create success/failure popup on the frontend. | 2 | Complete
|  | T06 | Run unit tests & Gherkin | 2 | Complete
|  | T07 | Review Pull Request before Main branch merge | 2 | Complete
US010 | "As a registered and logged-in user with at least one Instagram account linked, I would like to view my personal content on my NF-TEA account." |  |  |  |  | TRUE
|  | T01 | Create Gherkin Script | 2 | Complete
|  | T02 | Create Instagram API queries to get user content. | 2 | Complete
|  | T03 | Create user profile page on the frontend. | 2 | Complete
| Dependent on US007 | T04 | Create content tab in the user profile page on the frontend. | 2 | Complete
|  | T05 | Create content table in the user profile page on the frontend. | 2 | Complete
|  | T06 | Run unit tests & Gherkin | 2 | Complete
|  | T07 | Review Pull Request before Main branch merge | 2 | Complete
US011 | "As a registered and logged-in user with at least one Instagram account linked, I would like to create NFTs based on my Instagram content." |  |  |  |  | TRUE
|  | T01 | Create Gherkin Script | 3 | Complete
|  | T02 | Create NFT smart contract model. | 3 | Complete
|  | T03 | Create frontend middleware functions to communicate with the smart contract. | 3 | Complete
|  | T04 | Create frontend NFT creation dialogue. | 3 | Complete
|  | T05 | Run unit tests & Gherkin | 3 | Complete
|  | T06 | Review Pull Request before Main branch merge | 3 | Complete
US012 | "As a registered and logged-in user, I would like to view my owned NFTs on my account." |  |  |  |  | TRUE
|  | T01 | Create Gherkin Script | 3 | Complete
|  | T02 | Implement function to query NFTs | 3 | Complete
|  | T03 | Display the NFT to the frontend | 3 | Complete
|  | T04 | Run unit tests & Gherkin | 3 | Complete
|  | T05 | Review Pull Request before Main branch merge | 3 | Complete
US013 | "As a registered and logged-in user with at least one NFT linked to my account, I would like to create a collection of NFTs." |  |  |  |  | TRUE
|  | T01 | Create Gherkin Script | 3 | Complete
|  | T02 | Implement function to add the NFT to a collection | 3 | Complete
|  | T03 | Display collection and options to frontend | 3 | Complete
|  | T04 | Run unit tests & Gherkin | 3 | Complete
|  | T05 | Review Pull Request before Main branch merge | 3 | Complete
US014 | "As a registered and logged-in user with at least one NFT collection linked to my account, I would like to edit what NFTs are included in the collection." |  |  |  |  | TRUE
|  | T01 | Create Gherkin Script | 3 | Complete
|  | T02 | Display edit options on NFT collection page | 3 | Complete
| Dependent on US011 | T03 | Implement function to edit what NFTs are included in collection | 3 | Complete
|  | T04 | Run unit tests & Gherkin | 3 | Complete
|  | T05 | Review Pull Request before Main branch merge | 3 | Complete
US015 | "As a registered and logged-in user with at least one NFT collection linked to my account, I would like to delete a collection from my account, keeping the NFTs." |  |  |  |  | TRUE
|  | T01 | Create Gherkin Script | 3 | Complete
|  | T02 | Implement function to delete collection and display a confirmation message | 3 | Complete
|  | T03 | Display delete button on collection page | 3 | Complete
|  | T04 | Run unit tests & Gherkin | 3 | Complete
|  | T05 | Review Pull Request before Main branch merge | 3 | Complete
US016 | "As a registered and logged-in user, I would like to view my personal NFT collection on my account." |  |  |  |  | TRUE
|  | T01 | Display collections on user account page | 3 | Complete
|  | T02 | Review Pull Request before Main branch merge | 3 | Complete
Note on G1: don't forget to give tasks to @Kiro:) -SMI_10

## Week 3 Task List
Please read comments attached to the tasks.
Story ID | Task ID | Task | Week | Status | Assignee | Estimated Effort | Effort | Peer Reviewed | Feature File
US011 | [7 empty] | TRUE | createNFT_IG.feature
| T01 | Create Gherkin Script | 3 | Complete | Ehsan, Dan | 3h | 3h
| T02 | Create NFT smart contract model. | 3 | Complete | Mircea | 3h | 4h
| T03 | Create frontend middleware functions to communicate with the smart contract. | 3 | Complete | Mircea | 2h | 4h
| T04 | Create frontend NFT creation dialogue. | 3 | Complete | Kiro, Dan | 3h | 7h
| T05 | Run unit tests & Gherkin | 3 | Complete | Seb | 30 min | 30 min
| T06 | Review Pull Request before Main branch merge | 3 | Complete | Seb | 1h | 1h
US012 | [7 empty] | TRUE | Goes with createNFT_IG.feature
| T01 | Create Gherkin Script | 3 | Complete | Abdelmadjid | 1h | 1h
| T02 | Implement function to query NFTs | 3 | Complete | Mircea | 2h | 3h
| T03 | Display the NFT to the frontend | 3 | Complete | Abdelmadjid | 2h | 4h
| T04 | Run unit tests & Gherkin | 3 | Complete | Abdelmadjid | 30 min | 1h
| T05 | Review Pull Request before Main branch merge | 3 | Complete | Seb | 1h | 1h
US013 | [7 empty] | TRUE | createNFT_collection.feature
addNFTCollection.feature
| T01 | Create Gherkin Script | 3 | Complete | Ehsan, Dan | 3h | 3h
| T02 | Implement function to add the NFT to a collection | 3 | Complete | Kiro, Dan | 2h | 2h
| T03 | Display collection and options to frontend. | 3 | Complete | Kiro, Dan | 1h | 1h
| T04 | Run unit tests & Gherkin | 3 | Complete | Seb | 30 min | 30 min
| T05 | Review Pull Request before Main branch merge | 3 | Complete | Seb | 1h | 1h
US014 | [7 empty] | TRUE | editCollection.feature
| T01 | Create Gherkin Script | 3 | Complete | Kalvin | 2h | 2h
| T02 | Display edit options on NFT collection page | 3 | Complete | Hong Yi | 2h | 2h
| T03 | Implement function to edit what NFTs are included in collection | 3 | Complete | Hong Yi | 45mins | 1h
| T04 | Run unit tests & Gherkin | 3 | Complete | Seb | 30 min | 30 min
| T05 | Review Pull Request before Main branch merge | 3 | Complete | Seb | 1h | 1h
US015 | [7 empty] | TRUE | deleteCollection.feature
| T01 | Create Gherkin Script | 3 | Complete | Kalvin | 1h | 1h
| T02 | Implement function to delete collection and display a confirmation message | 3 | Complete | Harsh | 1h | 1.5h
| T03 | Display delete button on collection page | 3 | Complete | Harsh | 1h | 1h
| T04 | Run unit tests & Gherkin | 3 | Complete | Seb | 30 min | 30 min
| T05 | Review Pull Request before Main branch merge | 3 | Complete | Seb | 1h | 1h
US016 | [7 empty] | TRUE | N/A (Only enables viewing of previous
| T01 | Display collections on user account page | 3 | Complete | Hong Yi | 1.5h | 1.5h |  | User Stories on frontend)
| T02 | Review Pull Request before Main branch merge | 3 | Complete | Seb | 30 min | 30 min
Note on C19: A COLLECTION BY DEFINITION IS LIKE AN ALBUM OF PHOTOS. THEREFORE IN OUR CONTEXT IT IS AN ALBUM OF YOUR OWNED NFTS. -Dan Hosi
Note on C20: (on user profile page, have a dedicated tab for ig content and nft content). -Dan Hosi