## Product Backlog
Story ID | User Story | Description | Priority | Refinement | Status
US001 | Create Account | "As a user, I would like to be able to create a NF-TEA Marketplace account." | This Sprint | Groomed | Not Started
US002 | Edit Account | "As a user, I would like to be able to edit my NF-TEA Marketplace account details." | This Sprint | Groomed | Not Started
US003 | Delete Account | "As a user, I would like to be able to delete my NF-TEA Marketplace account." | This Sprint | Groomed | Not Started
US004 | Login | "As a registered user, I would like to be able to login to my NF-TEA Marketplace account." | This Sprint | Groomed | Not Started
US005 | Logout | "As a registered and logged-in user, I would like to be able to logout from my NF-TEA Marketplace account." | This Sprint | Groomed | Not Started
US006 | Link MetaMask | "As a registered and logged-in user, I would like to be able to link my MetaMask wallet to my NF-TEA account." | This Sprint | Groomed | Not Started
US007 | Link Instagram account(s) | "As a registered and logged-in user, I would like to be able to link one or more Instagram accounts to my NF-TEA account." | This Sprint | Groomed | Not Started
US008 | Unlink MetaMast | "As a registered and logged-in user, I would like to unlink my previously-linked MetaMask wallet from my NF-TEA account." | This Sprint | Groomed | Not Started
US009 | Unlink Instagram account(s) | "As a registered and logged-in user, I would like to unlink my previously-linked Instagram account(s) from my NF-TEA account." | This Sprint | Groomed | Not Started
US010 | View personal Instagram content | "As a registered and logged-in user with at least one Instagram account linked, I would like to view my personal content on my NF-TEA account." | This Sprint | Groomed | Not Started
US011 | Create NFT based on Instagram | "As a registered and logged-in user with at least one Instagram account linked, I would like to create NFTs based on my Instagram content." | This Sprint | Groomed | Not Started
US012 | View owned NFTs | "As a registered and logged-in user, I would like to view my owned NFTs on my account." | This Sprint | Groomed | Not Started
US013 | Create NFT collection | "As a registered and logged-in user with at least one NFT linked to my account, I would like to create a collection of NFTs." | This Sprint | Groomed | Not Started
US014 | Edit NFT collection | "As a registered and logged-in user with at least one NFT collection linked to my account, I would like to edit what NFTs are included in the collection." | This Sprint | Groomed | Not Started
US015 | Delete NFT collection | "As a registered and logged-in user with at least one NFT collection linked to my account, I would like to delete a collection from my account, keeping the NFTs." | This Sprint | Groomed | Not Started
US016 | View personal NFT collection | "As a registered and logged-in user, I would like to view my personal NFT collection on my account." | This Sprint | Groomed | Not Started
US017 | Create NFT listing | "As a registed and logged-in user with at least one NFT linked to my account, I would like to create a listing on the marketplace to sell my NFT." | Next Sprint | Not groomed | Not Started
US018 | Edit NFT listing | "As a registered and logged-in user with an existing listing on my account, I would like to edit the listing." | Next Sprint | Not groomed | Not Started
US019 | Delete NFT listing | "As a registered and logged-in user with an existing listing on my account, I would like to delete the listing from the marketplace such that other users won't be able to buy it anymore." | Next Sprint | Not groomed | Not Started
US020 | View NFT listings on marketplace | "As a registered and logged-in user, I would like to be able to browse all the listings on the market place so that I can buy one if I like it." | Next Sprint | Not groomed | Not Started
US021 | Search for NFTs on marketplace | "As a registered and logged-in user, I would like to be able to search for a specific NFT by its name, its collection or its owner." | Next Sprint | Not groomed | Not Started
US022 | Sort NFT marketplace listings | "As a registered and logged-in user, I would like to be able to filter my searched items so that I can easily browse through them." | Next Sprint | Not groomed | Not Started
US023 | Receive confirmation message that NFT sold | "As a registered user, I would like to be able to receive a confirmation message on my account that my NFT has been sold on the Marketplace and the funds are deposited." | Next Sprint | Not groomed | Not Started
US024 | Receive receipt message that NFT purchase successsful | "As a registered and logged-in user, I would like to receive a receipt of my purchase when I buy an NFT." | Next Sprint | Not groomed | Not Started
US025 | Watchlist NFT(s) | "As a registered and logged-in user, I would like to be able to watchlist an NFT ("favorite") to a list to keep track of its status." | Next Sprint | Not groomed | Not Started
US026 | Day/Night Mode | "As a user of NF-TEA, I would like to be able to have light and dark mode to suit my preferences." | Next Sprint | Not groomed | Not Started
US027 | Send trade offer | "As a registered and logged-in user, I would like to be able to submit a trade offer to another marketplace user." | Next Sprint | Not groomed | Not Started
US028 | Accept/Decline trade offer | "As a registered and logged-in user, I would like to be able to accept or decline a trade offer from a marketplace user." | Next Sprint | Not groomed | Not Started
US029 | Receive notification of trade offer | "As a registered user, I would like to be able to receive notifications of trade offers so that I can accept or refuse them" | Next Sprint | Not groomed | Not Started
US030 | Receive notification of trade offer status | "As a registered user, I would like to be able to see the trade offer status so that I can know if the trade is still on" | Next Sprint | Not groomed | Not Started
US031 | Search for users on marketplace | "As a registered user, I would like to be able to search for other users on the market place so that I send them trade offers" | Next Sprint | Not groomed | Not Started
US032 | View other users' public accounts | "As a registered and logged-in user, I would like to be able to view other people's accounts so that I can send them a trade offers" | Next Sprint | Not groomed | Not Started
US033 | Manage marketplace | "As an administrator, I would like to manage NFT listings, user accounts, and validate new accounts" | Next Sprint | Not groomed | Not Started
US034 | Create Discounts on NFT listings | "As a registered and logged-in user, I would like to create temporary discounts on my NFT listings on the marketplace." | Next Sprint | Not groomed | Not Started
US035 | Process marketplace tranasction fees | "As the marketplace owner, I would like to receive 2% of each transaction amount on the business wallet. | Next Sprint | Not groomed | Not Started
US036 | NFT Royalties option to original owner | "As a registered and logged-in user and a first seller of an NFT, I would like to receive a portion of the sales on any future transaction of my NFT so that I gain money on my wallet." | Next Sprint | Not groomed | Not Started

## Sprint A Backlog
Story ID | User Story Description | Task ID | Task | Week | Status | Assignee | Feature File | Reviewer | Peer Reviewed
SETUP | Setup (every developer) | [7 empty] | FALSE
|  | T01 | Create Umple class model | 1 | Not started | @Everyone
|  | T02 | Create CRUD Repositories | 1 | Not started | @Everyone
|  | T03 | Test CRUD Repositories (unit) | 1 | Not started | @Everyone
|  | T04 | Decide what pages/views should different users see. | 1 | Not started | @Everyone
|  | T05 | Create frontend mock up of each page/view that a user can see | 1 | Not started | @Everyone, @Dan, @Mircea
|  | T06 | Implement the mock ups of each page/views. | 1 | Not started | @Everyone
|  | T07 | Create Vue project. | 1 | Not started | @Mircea
US001 | "As a user, I would like to be able to create a NF-TEA Marketplace account." | [7 empty] | FALSE
|  | T01 | Create Gherkin Script | 1 | Not started | @Majid
|  | T02 | Create account creation frontend page | 1 | Not started | @Majid
|  | T03 | Include scripts and logic for webpage to create account | 1 | Not started | @Majid
|  | T04 | Run unit tests & Gherkin | 1 | Not started | @Majid
|  | T05 | Review Pull Request before Main branch merge | 1 | Not started | @Seb
US002 | "As a user, I would like to be able to edit my NF-TEA Marketplace account details." | [7 empty] | FALSE
|  | T01 | Create Gherkin Script | 1 | Not started | @Ehsan
|  | T02 | Create account edit frontend page | 1 | Not started | @Ehsan
|  | T03 | Include scripts and logic for webpage to edit a user's account | 1 | Not started | @Ehsan
|  | T04 | Run unit tests & Gherkin | 1 | Not started | @Ehsan
|  | T05 | Review Pull Request before Main branch merge | 1 | Not started | @Seb
US003 | "As a user, I would like to be able to delete my NF-TEA Marketplace account." | [7 empty] | FALSE
|  | T01 | Create Gherkin Script | 1 | Not started | @Kiro
|  | T02 | Create Delete Account Button in the Account tab page. | 1 | Not started | @Mircea
|  | T03 | Implement backend logic to remove the account from the database. | 1 | Not started | @Mircea
|  | T04 | Create a text box that takes in the user's password and only then allows the user to delete. | 1 | Not started | @Kiro
|  | T05 | Decide what happens to the user's NFTs when account is deleted. | 1 | Not started | @Mircea
|  | T06 | Run unit tests & Gherkin | 1 | Not started | @Kiro
|  | T07 | Review Pull Request before Main branch merge | 1 | Not started | @Seb
US004 | "As a registered user, I would like to be able to login to my NF-TEA Marketplace account." | [7 empty] | FALSE
|  | T01 | Create Gherkin Script | 1 | Not started | @Kalvin
|  | T02 | Create a login page for users to login with their email. | 1 | Not started | @Kalvin
|  | T03 | Implement logic to query if the user email exists in the database. | 1 | Not started | @Kalvin
|  | T04 | If user email exists in database, check if the password entered is correct. | 1 | Not started | @Kalvin
|  | T05 | Display a message in the case of invalid username/password. | 1 | Not started | @Hong Yi
|  | T06 | Display a message in the case an account is locked out | 1 | Not started | @Hong Yi
|  | T07 | Implement logic to bring the user to their account home page. | 1 | Not started | @Hong Yi
|  | T08 | Run unit tests & Gherkin | 1 | Not started | @Hong Yi
|  | T09 | Review Pull Request before Main branch merge | 1 | Not started | @Seb
US005 | "As a registered and logged-in user, I would like to be able to logout from my NF-TEA Marketplace account." | [7 empty] | FALSE
|  | T01 | Create Gherkin Script | 1 | Not started | @Harsh
|  | T02 | Create a logout button on top nav menu | 1 | Not started | @Harsh
|  | T03 | Implement backend logic to log out the current user and return to homepage | 1 | Not started | @Harsh
|  | T04 | Run unit tests & Gherkin | 1 | Not started | @Harsh
|  | T05 | Review Pull Request before Main branch merge | 1 | Not started | @Seb
US006 | "As a registered and logged-in user, I would like to be able to link my MetaMask wallet to my NF-TEA account." | [7 empty] | FALSE
|  | T01 | Create Gherkin Script | 2 | Not started
|  | T02 | Add Metamask library to frontend. | 2 | Not started | @Mircea
|  | T03 | Create connect to Metamask button on the frontend. | 2 | Not started
|  | T04 | Create success/failure popup on the frontend. | 2 | Not started
|  | T05 | Run unit tests & Gherkin | 2 | Not started
|  | T06 | Review Pull Request before Main branch merge | 2 | Not started | @Seb
US007 | "As a registered and logged-in user, I would like to be able to link one or more Instagram accounts to my NF-TEA account." | [7 empty] | FALSE
|  | T01 | Create Gherkin Script | 2 | Not started
|  | T02 | Create Facebook NF-Tea project on Facebook API page | 2 | Not started | @Mircea
|  | T03 | Add all team members to the Facebook NF-Tea project. | 2 | Not started | @Mircea
|  | T04 | Create Facebook API queries. | 2 | Not started
|  | T05 | Create connect to Instagram button on the frontend. | 2 | Not started
|  | T06 | Create success/failure popup on the frontend. | 2 | Not started
|  | T07 | Run unit tests & Gherkin | 2 | Not started
|  | T08 | Review Pull Request before Main branch merge | 2 | Not started | @Seb
US008 | "As a registered and logged-in user, I would like to unlink my previously-linked MetaMask wallet from my NF-TEA account." | [7 empty] | FALSE
|  | T01 | Create Gherkin Script | 2 | Not started
|  | T02 | Create frontend dialogue to unlink Metamask. | 2 | Not started
|  | T03 | Implement function to communicate with Metamask for its disconnection. | 2 | Not started
|  | T04 | Create success/failure popup on the frontend. | 2 | Not started
|  | T05 | Run unit tests & Gherkin | 2 | Not started
|  | T06 | Review Pull Request before Main branch merge | 2 | Not started | @Seb
US009 | "As a registered and logged-in user, I would like to unlink my previously-linked Instagram account(s) from my NF-TEA account." | [7 empty] | FALSE
|  | T01 | Create Gherkin Script | 2 | Not started
|  | T02 | Create disconnect to Instagram button on the frontend. | 2 | Not started
|  | T03 | Create frontend dialogue to unlink Instagram. | 2 | Not started
|  | T04 | Create Facebook API disconnect queries. | 2 | Not started
|  | T05 | Create success/failure popup on the frontend. | 2 | Not started
|  | T06 | Run unit tests & Gherkin | 2 | Not started
|  | T07 | Review Pull Request before Main branch merge | 2 | Not started | @Seb
US010 | "As a registered and logged-in user with at least one Instagram account linked, I would like to view my personal content on my NF-TEA account." | [7 empty] | FALSE
|  | T01 | Create Gherkin Script | 2 | Not started
|  | T02 | Create Instagram API queries to get user content. | 2 | Not started
|  | T03 | Create user profile page on the frontend. | 2 | Not started
|  | T04 | Create content tab in the user profile page on the frontend. | 2 | Not started
|  | T05 | Create content table in the user profile page on the frontend. | 2 | Not started
|  | T06 | Run unit tests & Gherkin | 2 | Not started
|  | T07 | Review Pull Request before Main branch merge | 2 | Not started | @Seb
US011 | "As a registered and logged-in user with at least one Instagram account linked, I would like to create NFTs based on my Instagram content." | [7 empty] | FALSE
|  | T01 | Create Gherkin Script | 3 | Not started
|  | T02 | Create NFT smart contract model. | 3 | Not started | @Mircea
|  | T03 | Create frontend middleware functions to communicate with the smart contract. | 3 | Not started
|  | T04 | Create frontend NFT creation dialogue. | 3 | Not started
|  | T05 | Run unit tests & Gherkin | 3 | Not started
|  | T06 | Review Pull Request before Main branch merge | 3 | Not started | @Seb
US012 | "As a registered and logged-in user, I would like to view my owned NFTs on my account." | [7 empty] | FALSE
|  | T01 | Create Gherkin Script | 3 | Not started
|  | T02 | Implement function to query NFTs | 3 | Not started
|  | T03 | Display the NFT to the frontend | 3 | Not started
|  | T04 | Run unit tests & Gherkin | 3 | Not started
|  | T05 | Review Pull Request before Main branch merge | 3 | Not started | @Seb
US013 | "As a registered and logged-in user with at least one NFT linked to my account, I would like to create a collection of NFTs." | [7 empty] | FALSE
|  | T01 | Create Gherkin Script | 3 | Not started
|  | T02 | Implement function to add the NFT to a collection | 3 | Not started
|  | T03 | Display collection and options to frontend | 3 | Not started
|  | T04 | Run unit tests & Gherkin | 3 | Not started
|  | T05 | Review Pull Request before Main branch merge | 3 | Not started | @Seb
US014 | "As a registered and logged-in user with at least one NFT collection linked to my account, I would like to edit what NFTs are included in the collection." | [7 empty] | FALSE
|  | T01 | Create Gherkin Script | 3 | Not started
|  | T02 | Display edit options on NFT collection page | 3 | Not started
|  | T03 | Implement function to edit what NFTs are included in collection | 3 | Not started
|  | T04 | Run unit tests & Gherkin | 3 | Not started
|  | T05 | Review Pull Request before Main branch merge | 3 | Not started | @Seb
US015 | "As a registered and logged-in user with at least one NFT collection linked to my account, I would like to delete a collection from my account, keeping the NFTs." | [7 empty] | FALSE
|  | T01 | Create Gherkin Script | 3 | Not started
|  | T02 | Implement function to delete collection and display a confirmation message | 3 | Not started
|  | T03 | Display delete button on collection page | 3 | Not started
|  | T04 | Run unit tests & Gherkin | 3 | Not started
|  | T05 | Review Pull Request before Main branch merge | 3 | Not started | @Seb
US016 | "As a registered and logged-in user, I would like to view my personal NFT collection on my account." | [7 empty] | FALSE
|  | T01 | Display collections on user account page | 3 | Not started
|  | T02 | Review Pull Request before Main branch merge | 3 | Not started | @Seb
Note on G1: don't forget to give tasks to @Kiro:) -SMI_10